## Role & Responsibility
Role | Owner | Owns | Deliverable by 8 Nov
1. Domain and product lead |  | Shared data shapes, tool contracts, schedule, integration, demo script, contribution log | Demo, README, final report
2. Knowledge and memory |  | Scheme collection (URL and date), clause splitting, retrieval, memory policy | 40 schemes, retrieval evaluation (Recall@5), memory policy
3. Agents and orchestration |  | LangGraph graph, supervisor, intake and eligibility agents, Reflexion loop | Working graph with resume, single-agent baseline
4. Tools, control and security |  | MCP servers, approval gate, hooks, guardrails, threat model | Tool list and tests, approval gate, threat model
5. Evaluation and red team |  | Golden set, 60 personas, 30+ attacks, judge calibration, experiment results | Evaluation report, red-team results
6. Deployment and operations |  | FastAPI app and UI, Docker Compose, CI eval gate, Grafana dashboard and alert | Running app, CI run, alert demo

## First week(24 oct to 31 oct)
Task | Status | Comment
First-week tasks (24 Oct to 31 Oct)
Digvijay: draft HouseholdProfile, Verdict, and SchemeRecord for the team to review by 27 Oct. | Done
Snehal: start collecting schemes from myScheme and ministry PDFs, with URL and date for each. Target: 20 by 31 Oct.
Saurabh/Satya: build the LangGraph skeleton with mock tools, Memory
Sharika: finish the rule-engine tests and write the tool list with read or write marks.
Name: set up the FastAPI skeleton and a draft CI workflow. Install Docker on the server.
Name: Grafana dashboard - Monitoring
Digvijay (Shows interest during the standup meeting) - Persona-to-profile adapter - 29 Oct | Done | Write a small function that turns a persona or household test case's profile_facts into the rule fields (for example respondent_age to age). Add --persona-id to graph.run so a persona can be used instead of --citizen.
Digvijay Chat UI Interface for Chat Conversation | Inprogress